Procurement Timeline (estimated)

| When | What | Who\ Notes |
| --- | --- | --- |
| Oct – Dec 2013 | Gather Requirements | Business Unit / Project Management Team |
| Jan 2014 | Develop TORFP | Business Unit / Project Management Team / IT Division / Procurement |
| Feb 2014 | Internal reviews / updates / approval | Division Managers / Business Unit / Project Management Team / IT Division / Procurement |
| 3/15/14 | TORFP approved | DoIT |
| 3/17/14 | Publish TORFP to vendors (Includes scheduling the pre-proposal review meeting). | Procurement |
| 3/31/14 | Pre-Bid Conference | Procurement, Evaluation Committee if possible, Project Sponsors (business & OIT) |
| 4/16/14 | Evaluation Committee Kick-off meetings (discuss & finalize) - Role & responsibilities - Map out dates for vendor presentations - Review TORFP - Evaluation criteria and weighting - Review draft Evaluation tool - Reference Check questions - Vendor presentation/interview process, timeline, activities | Evaluation Committee |
| 4/21/14 2pm | Vendor Proposals due to agency (min. 20 bus. Days – includes 2 holidays) | Procurement to distribute to Evaluation Committee |
| 4/24/14 | Schedule Vendor Interviews ( see date and time below) | Procurement (once the number of vendors is known) |
| 4/23/14 – 5/13/14 | Review Technical Proposal & identify questions - Questions for each vendor will be compiled and sent to the vendor prior to the specific vendor presentation - Vendor will not be required to respond in writing prior to the presentation – written responses to these questions and others that arise during the meeting will be due post- presentation meeting. | Evaluation Committee |
| 5/19/14 am | Vendor Interviews - 30 min interview - No presentation - Discuss questions that were identified in step 6. - May require additional documentation to be provided post-presentation by the Dev vendor - Best and Final Offer (BAFO) Financial Proposal will be requested post -presentation Post Vendor presentation wrap-up 15 min round robin discussion of scores to hear the feedback from everybody as they make their final decisions Goal is to complete the bulk of each vendor’s evaluation form during the wrap-up. | Evaluation Committee Each review is estimated for 45 min: - 30 min vendor - 15 wrap-up Company A: 8:30-9:30 Company B: 9:30 -10:30 Evaluation forms (hard-copies will be available for completion during each vendor session. Soft-copies will be sent as well.) |
| 5/20/14 – 5/22/14 | Reference Checks - Evaluation Committee to revise evaluations (Company points) based on results of reference checks | Shared responsibility by the evaluation committee |
| 5/25/14 | All vendor responses due - Responses to questions - BAFO | Procurement distributes responses to questions to the Evaluation Committee |
| 5/28/14 | Evaluation review finalized for each vendor - Revise previously completed evaluation forms based on written responses | Evaluation Committee |
| 5/28/14 | Summation of Vendor Technical Evaluations | Evaluation Committee Chairperson |
| 5/28/14 | Summation of Vendor Technical Evaluations & Financial Proposals | Procurement |
| 5/29/14 | Vendor selection – recommendation to DoIT | Procurement |
| TBD –estimated for up to 4 weeks | Notice to proceed - DoIT approval - Vendor notified - TOA completed and signed - PO completed - DoIT approval of PO - Start date communicated to Vendor | DBM Procurement |