## Sheet1
Attachment # 21 CATS + FA 13 Construction Schedule Persimmon Tree and Rockefeller Court Equipment Shelters
Line | Item | Vendor submitted schedule | Date requirements (calendar days)
-------- | Notice to proceed [NTP] (Provided by DoIT with approved purchase order) | ----------------------------------- | 120
1 | Clearing and Grading |  | NTP + Days
2 | Shelter Foundation Poured |  | NTP + # Days
3 | Shelter Delivery |  | NTP + # Days
4 | Final Grounding (will trigger request for R56 and punch list inspection) |  | NTP + # Days
5 | Site Completion (to include punch list and R56 corrections) |  | NTP + # Days
6 | Closeout documents submitted for state review |  | NTP + # Days
Vendor Signature:
Instructions: Vendors will submit this document with their signed/sealed bid proposal. Construction completion will be used to compare and evaluate supplied bids. The submitted schedule will also serve as the contractor's binding schedule for the project. Projects not completed within the scheduled completion shown on the schedule will be subject to an assessment for liquidated damages. The vendor will write the number of days past the NTP in the boxes provided.