## Sheet1
Attachment # 21 CATS + FA 13 Construction Schedule Table Rock SHA Communications Tower
Line | Item | TO Contractor submitted schedule | Date requirements (Business Days)
-------- | Notice to proceed [NTP] (Provided by DoIT with approved purchase order) | ----------------------------------- | ------------------------
1 | Clearing and Grading |  | NTP + # Days
2 | Shelter/Tower Foundation poured |  | NTP + # Days
3 | Tower Delivery |  | NTP + # Days
4 | Shelter Delivery |  | NTP + # Days
5 | Tower Erection (will trigger request for tower inspection) |  | NTP + # Days
6 | Final Grounding (will trigger request for R56 and punch list inspection) |  | NTP + # Days
7 | Site Completion (to include punch list and R56 corrections) |  | NTP + # Days
8 | Closeout documents submitted for state review |  | NTP + # Days
TO Contractor Signature
Instructions: TO Contractors will submit this document with their signed/sealed bid proposal. Construction completion will be used to compare and evaluate supplied bids. The submitted schedule will also serve as the contractor's binding schedule for the project. Projects not completed within the scheduled completion shown on the schedule will be subject to an assessment for liquidated damages. The TO Contractor will write the number of days past the NTP in the boxes provided.